## Project Plan
Phase | Module / Task | Estimated Duration | Working Days (Approx)
Phase 1 – Planning & Architecture | Database Design | 2–3 Weeks | 20
Phase 1 – Planning & Architecture | System Architecture | 2–3 Weeks | 20
Phase 1 – Planning & Architecture | UI/UX Design (All Apps) | 2–3 Weeks | 20
Phase 1 – Planning & Architecture | API Structure | 2–3 Weeks | 20
Phase 1 – Planning & Architecture | Server Setup | 2–3 Weeks | 20
Phase 2 – Core Development | Backend Development | 6–8 Weeks | 60
Phase 2 – Core Development | Authentication (Google/Apple/International Login) | 6–8 Weeks | 60
Phase 2 – Core Development | Order System | 6–8 Weeks | 60
Phase 2 – Core Development | Vendor Management | 6–8 Weeks | 60
Phase 2 – Core Development | Driver Management | 6–8 Weeks | 60
Phase 2 – Core Development | Transactions | 6–8 Weeks | 60
Phase 2 – Core Development | Ratings | 6–8 Weeks | 60
Phase 2 – Core Development | Cooking Request Logic | 6–8 Weeks | 60
Phase 2 – Core Development | Combo Meals | 6–8 Weeks | 60
Phase 2 – Core Development | Admin Panel APIs | 6–8 Weeks | 60
Phase 2 – Core Development | Push Notifications | 6–8 Weeks | 60
Phase 2 – Core Development | Payment Gateway | 6–8 Weeks | 60
Phase 2 – Core Development | Security (VPN/Mock Detection) | 6–8 Weeks | 60
Phase 2 – Core Development | Customer App Development | 6–8 Weeks | 60
Phase 2 – Core Development | Menu + Filters | 6–8 Weeks | 60
Phase 2 – Core Development | Cart + Related Products | 6–8 Weeks | 60
Phase 2 – Core Development | Order Tracking | 6–8 Weeks | 60
Phase 2 – Core Development | Discounts | 6–8 Weeks | 60
Phase 2 – Core Development | Chat | 6–8 Weeks | 60
Phase 2 – Core Development | Past Orders | 6–8 Weeks | 60
Phase 2 – Core Development | Driver App Login | 6–8 Weeks | 60
Phase 2 – Core Development | Task List | 6–8 Weeks | 60
Phase 2 – Core Development | Live Tracking | 6–8 Weeks | 60
Phase 2 – Core Development | Driver Chat | 6–8 Weeks | 60
Phase 2 – Core Development | Earnings | 6–8 Weeks | 60
Phase 2 – Core Development | Fake Location Protection | 6–8 Weeks | 60
Phase 2 – Core Development | Vendor Orders | 5–7 Weeks | 40
Phase 2 – Core Development | Menu Management | 5–7 Weeks | 40
Phase 2 – Core Development | Vendor Transactions | 5–7 Weeks | 40
Phase 2 – Core Development | Reports | 5–7 Weeks | 40
Phase 3 – Advanced Features | Foodics Integration | 3–4 Weeks | 26 | SEPARATE 26 DAYS AFTER COMPLETION
Phase 3 – Advanced Features | iOS Driver App (Separate Build) | 3–4 Weeks | 26
Phase 3 – Advanced Features | Admin Dashboard Analytics | 3–4 Weeks | 26
Phase 3 – Advanced Features | Performance Optimization | 3–4 Weeks | 26
Phase 3 – Advanced Features | Security Hardening | 3–4 Weeks | 26
Complete development from scratch, executed by a team of 13 members, is projected to require approximately 90–100 working days

## BUGS FIXING
S.No | Task Description | Estimated Man-Days
1 | Product rating on delivered & past orders | 3
2 | Menu filters enhancement | 4
3 | Product-wise percentage discount (no promo code) | 5
4 | Remove cutlery option & reflect across systems | 4
5 | Related products on cart screen | 3
6 | Driver App in iOS | 15
7 | Fix task list multiple click loading issue | 2
8 | Driver fake rider / VPN / mock location fix | 6
9 | Driver-Customer chat implementation | 6
10 | Vendor panel UI redesign (Zomato/Talabat style) | 8
11 | Verified / Unverified tags in dine-out comments | 2
12 | Vendor app transactions correction | 3
13 | Foodics integration | 10
14 | Google & Apple signup integration | 4
15 | International number login support | 3
16 | Cooking request at item level | 4
17 | Khedmah Daily Combo meals | 5
| Total Man-Days | 87
Bug resolution with a team of three members is estimated to take approximately 87–90 working days